## Sheet1
Timeline For Minor Project
Tasks | Week 1 (22 - 28 March) | [6 empty] | Week 2 (29 - 4 March)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Creating Schema and Models
Integrating Database with Back-End
Creating APIs
Testing APIs
Integrating Back-End with Front-End | [14 empty] | Chetan
Neelam
Akshat
Unit Testing | [14 empty] | Mohit
Integration Testing
System Testing
Documentation